## Sheet1
Listing search - refinements
| Search from the home page |  | 2
| search from the current search page |  | 1
refinements
|  | Populating all the filters | 1
|  | food Type | 1
|  | Cost | 1
|  | Taste | 1
|  | Rating | 1
|  | Nearby | 1
Inbox
| Reply |  | 2
| Approval |  | 2
| MailBox |  | 2
User feedback
| Rating |  | 3
| reviews |  | 3
Connect
Facebook connect
| Linkedin Connect | Login using social plugin | 5
|  | session user information | 3
|  | save information in DB- refer HIFI | 3
|  | Joined site notification - Mail | 2
Master Page
| Current user information |  | 3
| Login logout |  | 3
Testing
| Senario as consumer |  | 10
| Senario as requestor |  | 10

## 31-01-2013
Connect System to Internet DB | Done | when the review count is zero then hide the reviews 0 button
Modify the listing review DB | Done
business layer for Comments and ratings | Done
Modify Listing query to include the reviews | Done
create the Comment and rating Tab | done
Modify the CSS for the comments | Not Completed

## 01-02-2013
Clean up TFS and make proper structure | Done | TFS keeps the track for all the changes, so when something goes wrong please check it
Modify the CSS for the comments | Not Done | when modifying the mapped path solution, don’t forget to take the backup of exisitng folder
Set the ratings when the page loads | Not Done
when clicking on the reiview count on listings page , user should get redireted to the details listing page and the user scrolls down to the listing

## Sheet2
user Profile display | 2013-02-12
User Profile Edit | 2013-02-12
DashBoard main page with submenu | 2013-02-11
Listings in dashboard | 2013-02-11
requested approved listings in dashboard | 2013-02-13
Add Edit user profile to dash board | 2013-02-13